## Definitions
Risk Register — Definitions
Likelihood Levels
Level | Score | Description
Almost Certain | 5 | Expected to occur in most circumstances; has happened repeatedly in similar contexts.
Likely | 4 | Will probably occur; strong evidence or history of occurrence.
Possible | 3 | Could occur at some point; some evidence or precedent exists.
Unlikely | 2 | Not expected, but could occur under unusual circumstances.
Rare | 1 | May only occur in exceptional circumstances; very low probability.
Consequence Levels
Level | Score | Description
Catastrophic | 5 | Complete project failure, serious injury, or total loss of key deliverable.
Major | 4 | Significant impact on project objectives, timeline, or safety; major rework required.
Moderate | 3 | Noticeable impact; some rework, delay, or reduced quality, but recoverable.
Minor | 2 | Small impact easily addressed with minimal effort or cost.
Insignificant | 1 | Negligible impact; no meaningful effect on project outcomes.
Risk Score Calculation
Risk Score = Likelihood Score + Consequence Score
Risk Levels
Risk Level | Score Range | Interpretation
Low | 2 – 4 | Acceptable risk; manage through routine procedures.
Moderate | 5 – 6 | Monitor closely; implement mitigation measures where practical.
Significant | 7 | Requires active management and a documented mitigation plan.
High | 8 – 9 | Unacceptable without immediate mitigation; escalate to project lead.
Extreme | 10 | Critical risk; stop activity until risk is reduced or eliminated.
Key Terms
Term |  | Definition
Risk | An uncertain event or condition that, if it occurs, could have a positive or negative effect on one or more project objectives.
Likelihood | The probability of the risk event occurring, rated on a 5-point scale from Rare (1) to Almost Certain (5).
Consequence | The severity of impact if the risk event occurs, rated on a 5-point scale from Insignificant (1) to Catastrophic (5).
Risk Score | A numerical value calculated by adding the Likelihood score and the Consequence score (range: 2–10).
Risk Level | A qualitative classification (Low to Extreme) derived from the Risk Score.
Mitigation Measures | Actions planned or taken to reduce the likelihood or consequence of a risk.
Residual Risk | The remaining level of risk after mitigation measures have been applied.
Risk Area | The category to which the risk belongs (e.g., Mechanical, Electrical, Safety/WHS, Project Management).

## Risk Register
|  |  |  | Columns F, H, I, J auto populates |  |  |  |  | Be detailed in measures. Most areas will have 3 to 5 mitigations required. |  | Columns M,O,P, Q auto populates
Risk ID | Risk Area | Risk Description | Likelihood (Select from pull down) | Score | Consequence (Select from pull down) | Score | Risk Score | Level of Risk | Mitigation measures | RESIDUAL Likelihood (Select from pull down) | Score | RESIDUAL Consequence (Select from pull down) | Score | Risk Score | RESIDUAL Level of Risk
1 | Mechanical | Drivetrain belt or chain slips during pedalling, resulting in sudden loss of resistance and potential injury to the user. | Unlikely | 2 | Minor | 2 | 4 | Low | Install a protective guard over all moving belt/chain components. Conduct a mechanical inspection before each use or public event. Provide a safety briefing to all users prior to operation. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
2 | Electrical | Generator produces insufficient power output to charge the battery and supply the USB port, resulting in failure to meet core project objectives. | Possible | 3 | Moderate | 3 | 6 | Moderate | Research and select a generator rated for the required wattage. Benchmark power output requirements against realistic pedalling speeds. | Unlikely | 2 | Minor | 2 | 4 | Low
|  | Blender coupling mechanism fails to engage with the drivetrain correctly, resulting in the blender not functioning during outreach events. | Possible | 3 | Major | 4 | 7 | Significant | Test the coupling mechanism before event deployment. Document a standard step-by-step assembly and connection procedure. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
|  | The selected generator may require a higher shaft speed than can be achieved under realistic pedalling conditions, resulting in insufficient electrical output for battery charging and USB supply. | Possible | 3 | Major | 4 | 7 | Significant | Benchmark expected generator output against realistic pedalling and wheel speeds. Consider alternative transmission methods to increase generator shaft speed. Retain alternative generator candidates during the preliminary design stage. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
|  | Purchased components may not fit the available mounting space or interface properly with the prototype structure, resulting in rework, additional fabrication, or delay to assembly. | Possible | 3 | Moderate | 3 | 6 | Moderate | Check component dimensions and mounting requirements before purchase. Compare component size against the available frame and panel space. Prefer components with simple mounting arrangements during early prototype development. | Unlikely | 2 | Insignificant | 1 | 3 | Low
|  | Incorrect selection of fuse, switch, wiring, or connector types may result in overheating, short circuit, unreliable operation, or insufficient electrical protection. | Possible | 3 | Moderate | 3 | 6 | Moderate | Select protection and wiring components based on expected voltage and current levels. Use insulated stranded wire and suitable DC terminals for all connections. Review fuse ratings and wiring arrangements before prototype assembly. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
3 | Safety/ WHS | Exposed electrical components contact water or a user at an outdoor event, resulting in electric shock or system damage. | Unlikely | 2 | Major | 4 | 6 | Moderate | Conduct a WHS inspection of the unit before each public event. Ensure all team members complete the required workshop safety induction. Label all electrical hazard areas with appropriate warning signage. | Rare | 1 | Moderate | 3 | 4 | Low
|  | Improper battery selection, storage, or charging practice may create risks of short circuit, overheating, or non-compliance with school battery management requirements. | Unlikely | 2 | Major | 4 | 6 | Moderate | Use a sealed off-the-shelf battery or a battery with built-in protection where possible. Follow the school battery management protocol for purchasing, storage, and charging. Ensure battery terminals are protected and that charging arrangements are reviewed before use. | Rare | 1 | Moderate | 3 | 4 | Low
4 | Project Management | Team members are unable to complete assigned tasks on schedule due to competing academic workloads, resulting in delayed audit submissions. | Possible | 3 | Major | 4 | 7 | Significant | Set internal task deadlines one week ahead of each audit submission. Review the project schedule and risk register at every weekly meeting. Distribute tasks equitably based on each team member's availability. | Unlikely | 2 | Minor | 2 | 4 | Low
|  | Purchased components may not meet final design requirements, resulting in return or replacement delays, additional cost, and postponed prototype integration. | Unlikely | 2 | Major | 4 | 6 | Moderate | Review datasheets and interface requirements before purchase. Compare alternative suppliers and candidate components for major items. Prioritise off-the-shelf components with clearly stated specifications and dimensions. | Rare | 1 | Major | 4 | 5 | Moderate
5
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
DO NOT COMPLETE MORE THAN 50 ROWS

## Risk Matrix
Risk Assessment Matrix
Risk Score = Likelihood + Consequence
CONSEQUENCE
|  | Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Catastrophic (5)
LIKELIHOOD | Almost Certain (5) | 6 Moderate | 7 Significant | 8 High | 9 High | 10 Extreme
| Likely (4) | 5 Moderate | 6 Moderate | 7 Significant | 8 High | 9 High
| Possible (3) | 4 Low | 5 Moderate | 6 Moderate | 7 Significant | 8 High
| Unlikely (2) | 3 Low | 4 Low | 5 Moderate | 6 Moderate | 7 Significant
| Rare (1) | 2 Low | 3 Low | 4 Low | 5 Moderate | 6 Moderate
Risk Level Legend
Low | Score: 2 – 4
Moderate | Score: 5 – 6
Significant | Score: 7
High | Score: 8 – 9
Extreme | Score: 10