## Definitions
Risk Register — Definitions
Likelihood Levels
Level | Score | Description
Almost Certain | 5 | Expected to occur in most circumstances; has happened repeatedly in similar contexts.
Likely | 4 | Will probably occur; strong evidence or history of occurrence.
Possible | 3 | Could occur at some point; some evidence or precedent exists.
Unlikely | 2 | Not expected, but could occur under unusual circumstances.
Rare | 1 | May only occur in exceptional circumstances; very low probability.
Consequence Levels
Level | Score | Description
Catastrophic | 5 | Complete project failure, serious injury, or total loss of key deliverable.
Major | 4 | Significant impact on project objectives, timeline, or safety; major rework required.
Moderate | 3 | Noticeable impact; some rework, delay, or reduced quality, but recoverable.
Minor | 2 | Small impact easily addressed with minimal effort or cost.
Insignificant | 1 | Negligible impact; no meaningful effect on project outcomes.
Risk Score Calculation
Risk Score = Likelihood Score + Consequence Score
Risk Levels
Risk Level | Score Range | Interpretation
Low | 2 – 4 | Acceptable risk; manage through routine procedures.
Moderate | 5 – 6 | Monitor closely; implement mitigation measures where practical.
Significant | 7 | Requires active management and a documented mitigation plan.
High | 8 – 9 | Unacceptable without immediate mitigation; escalate to project lead.
Extreme | 10 | Critical risk; stop activity until risk is reduced or eliminated.
Key Terms
Term |  | Definition
Risk | An uncertain event or condition that, if it occurs, could have a positive or negative effect on one or more project objectives.
Likelihood | The probability of the risk event occurring, rated on a 5-point scale from Rare (1) to Almost Certain (5).
Consequence | The severity of impact if the risk event occurs, rated on a 5-point scale from Insignificant (1) to Catastrophic (5).
Risk Score | A numerical value calculated by adding the Likelihood score and the Consequence score (range: 2–10).
Risk Level | A qualitative classification (Low to Extreme) derived from the Risk Score.
Mitigation Measures | Actions planned or taken to reduce the likelihood or consequence of a risk.
Residual Risk | The remaining level of risk after mitigation measures have been applied.
Risk Area | The category to which the risk belongs (e.g., Mechanical, Electrical, Safety/WHS, Project Management).

## Risk Register
|  |  |  | Columns F, H, I, J auto populates |  |  |  |  | Be detailed in measures. Most areas will have 3 to 5 mitigations required. |  | Columns M,O,P, Q auto populates
Risk ID | Risk Area | Risk Description | Likelihood (Select from pull down) | Score | Consequence (Select from pull down) | Score | Risk Score | Level of Risk | Mitigation measures | RESIDUAL Likelihood (Select from pull down) | Score | RESIDUAL Consequence (Select from pull down) | Score | Risk Score | RESIDUAL Level of Risk
1 | Technical – OCR | OCR accuracy drops below the 85% target when processing low-quality or poorly scanned documents, resulting in incorrect or incomplete data extraction. | Possible | 3 | Major | 4 | 7 | Significant | Apply automated image pre-processing (denoising, deskewing, contrast enhancement) before OCR. Route low-quality scans to AWS Textract rather than Tesseract based on a quality assessment. Test the pipeline against a diverse benchmark dataset including noisy samples. Set a minimum quality threshold and flag documents below it for manual review. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
|  | Processing latency exceeds the 2-second target at the 95th percentile under normal load, causing the system to fail its performance objective. | Possible | 3 | Moderate | 3 | 6 | Moderate | Profile and optimise the OCR and parsing pipeline during development. Implement asynchronous request handling in FastAPI to allow concurrent document processing. Cache pre-processing outputs for repeated or similar document types. Conduct load testing before final evaluation to identify and resolve bottlenecks. | Unlikely | 2 | Minor | 2 | 4 | Low
2 | Data & Integration | Generated JSON output does not conform to the canonical schema, causing downstream API consumers at r2p to receive malformed or inconsistent data. | Possible | 3 | Major | 4 | 7 | Significant | Define and lock the canonical JSON schema at the design stage before development begins. Implement automated schema validation on every output before it is served through the API. Return a structured error response (HTTP 422) for any document that produces non-conforming output. Run regression tests against the schema after every pipeline change. | Unlikely | 2 | Minor | 2 | 4 | Low
|  | Clause-level source traceability metadata (page number, bounding box) is missing or inaccurate in the JSON output, making audit and compliance tracking unreliable. | Possible | 3 | Major | 4 | 7 | Significant | Embed page number and bounding box coordinates as required fields in the canonical JSON schema. Validate traceability fields are populated for every extracted clause before output is served. Include traceability checks in the automated test suite. Document the traceability mapping in the API specification. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
|  | External r2p systems are unable to integrate with the API due to undocumented or inconsistently structured endpoints, delaying adoption. | Unlikely | 2 | Moderate | 3 | 5 | Moderate | Use FastAPI automatic OpenAPI documentation generation and keep it current with all endpoints. Define and publish the API contract before integration testing begins. Version the API from the outset (e.g. /v1/) to prevent breaking changes. Conduct an integration test with a sample consumer before final delivery. | Rare | 1 | Minor | 2 | 3 | Low
3 | Security – Cybersecurity | Uploaded documents containing sensitive r2p contract data are accessed by unauthorised parties due to missing API authentication, resulting in a data breach. | Possible | 3 | Catastrophic | 5 | 8 | High | Implement API key or token-based authentication on all upload and retrieval endpoints before production. Restrict direct file system access; all access must go through authenticated API endpoints. Apply role-based access controls to separate read and write permissions. Log all access attempts with user identity, document ID, and timestamp for audit purposes. | Rare | 1 | Major | 4 | 5 | Moderate
|  | A malicious actor uploads a crafted document to exploit the OCR or parsing pipeline (e.g. embedded scripts, oversized payloads), causing system compromise or denial of service. | Unlikely | 2 | Major | 4 | 6 | Moderate | Validate file type, MIME type, and file size on every upload before processing begins. Sanitise all input filenames and reject files that do not match accepted formats. Run OCR and parsing in an isolated process with minimal system privileges. Set a hard document size limit (50 MB) and return HTTP 413 for oversized uploads. | Rare | 1 | Moderate | 3 | 4 | Low
|  | Lack of audit logging means document access and processing events cannot be traced, leaving the system non-compliant with r2p data governance requirements. | Possible | 3 | Major | 4 | 7 | Significant | Implement a structured audit log capturing document ID, submitting user, action type, and UTC timestamp. Store audit logs in an append-only format to prevent tampering. Include log retention and review procedures in system documentation. Test audit log completeness as part of the acceptance test plan. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
4 | Project Management | Testing is conducted only on synthetic documents because real r2p contracts are unavailable, meaning actual production accuracy may differ from reported PoC results. | Almost Certain | 5 | Moderate | 3 | 8 | High | Document the synthetic-data limitation clearly in the project report and evaluation section. Design synthetic test documents to closely replicate the format and layout of real r2p files. Recommend a production pilot using real documents as the first post-delivery action. Record test dataset characteristics so results can be reproduced when real data becomes available. | Likely | 4 | Minor | 2 | 6 | Moderate
|  | Team members are unable to complete assigned tasks on schedule due to competing academic workloads, resulting in delayed deliverables or an incomplete prototype. | Possible | 3 | Major | 4 | 7 | Significant | Set internal task deadlines one week ahead of each submission date. Review project schedule and task status at every weekly team check-in. Distribute tasks equitably and document responsibilities in the project charter. Maintain shared version control on GitHub so any team member can continue another's work if needed. | Unlikely | 2 | Moderate | 3 | 5 | Moderate
|  | The 12-week timeline is insufficient to deliver a fully production-ready system with authentication, containerisation, and load testing, resulting in an incomplete deployment. | Likely | 4 | Moderate | 3 | 7 | Significant | Scope the project explicitly as a Proof of Concept and define what is in and out of scope. Prioritise core pipeline features (OCR, parsing, JSON output, REST API) in early sprints. Defer non-essential features (Docker, user auth) to post-submission recommendations. Track sprint progress weekly and escalate scope risks to the industry mentor early. | Unlikely | 2 | Minor | 2 | 4 | Low
5 | Operational | AWS Textract costs exceed budget projections at production scale (above 10,000 pages/month), making the system financially unviable for r2p without renegotiation. | Unlikely | 2 | Moderate | 3 | 5 | Moderate | Monitor AWS Textract usage against the estimated cost of ~AUD 22/month per 10,000 pages. Route clean high-quality documents to free Tesseract and reserve Textract for noisy scans only. Set a monthly usage alert in AWS to notify administrators before cost thresholds are exceeded. Include cost modelling assumptions in project documentation for r2p budget planning. | Rare | 1 | Minor | 2 | 3 | Low
|  | The system has not been containerised or load-tested, meaning a production deployment may fail under real document volumes or in r2p's cloud environment. | Possible | 3 | Major | 4 | 7 | Significant | Recommend Docker containerisation and cloud deployment as short-term post-PoC actions in the report. Document all environment dependencies (Python version, libraries, API keys) to simplify future deployment. Design the FastAPI layer to be stateless so horizontal scaling can be added without re-architecture. Include a deployment checklist and infrastructure requirements in the final technical documentation. | Unlikely | 2 | Moderate | 3 | 5 | Moderate

## Risk Matrix
Risk Assessment Matrix
Risk Score = Likelihood + Consequence
CONSEQUENCE
|  | Insignificant (1) | Minor (2) | Moderate (3) | Major (4) | Catastrophic (5)
LIKELIHOOD | Almost Certain (5) | 6 Moderate | 7 Significant | 8 High | 9 High | 10 Extreme
| Likely (4) | 5 Moderate | 6 Moderate | 7 Significant | 8 High | 9 High
| Possible (3) | 4 Low | 5 Moderate | 6 Moderate | 7 Significant | 8 High
| Unlikely (2) | 3 Low | 4 Low | 5 Moderate | 6 Moderate | 7 Significant
| Rare (1) | 2 Low | 3 Low | 4 Low | 5 Moderate | 6 Moderate
Risk Level Legend
Low | Score: 2 – 4
Moderate | Score: 5 – 6
Significant | Score: 7
High | Score: 8 – 9
Extreme | Score: 10