## Risk Register
Risk ID | Risk Area | Risk Description | Likelihood | Score | Consequence | Score | Risk Score | Level of Risk | Mitigation Measures | Residual Likelihood | Score | Residual Consequence | Score | Residual Risk Score | Residual Level
1 | OCR Processing | Low-quality scanned documents reduce OCR accuracy | Possible | 3 | Major | 4 | 7 | Significant | Use image preprocessing; hybrid OCR (Tesseract + AWS Textract); testing datasets | Unlikely | 2 | Moderate | 3 | 5 | Moderate
2 | Project Schedule | 12-week timeline may not be sufficient | Possible | 3 | Major | 4 | 7 | Significant | Use Agile sprints; weekly milestones; progress tracking | Unlikely | 2 | Moderate | 3 | 5 | Moderate
3 | Testing Data | Lack of real company documents for testing | Likely | 4 | Moderate | 3 | 7 | Significant | Use synthetic datasets; request sample documents; increase testing | Possible | 3 | Minor | 2 | 5 | Moderate
4 | API Integration | API integration may fail with external systems | Possible | 3 | Moderate | 3 | 6 | Moderate | Use REST standards; integration testing; documentation | Unlikely | 2 | Minor | 2 | 4 | Low
5 | Security | Unauthorized access to document data | Possible | 3 | Major | 4 | 7 | Significant | Implement authentication; access control; encryption | Unlikely | 2 | Moderate | 3 | 5 | Moderate